## Sheet1
Estimate of Manhour & Material Costs
Task | Duration | Men | Man Days | Comments | Material costs £
Test Rack Design & Build
Design work | 15 | 1 | 15
Manufacture test rack | 20 | 1 | 20 | Includes cost of new rack | 3000
Sub-Station Equipment
One of each type of Panel Mounted Equipment | - | - | - | 6 items (£200 - £10500) | 12854
Internal Equipment to run Panel Equipment | - | - | - |  | 2000
Miscellaneous | - | - | - |  | 500
Room modifications
Modify Existing Dist Boards | 2 | 2 | 4 |  | 250
Test Rack Installed in R9 ?
Ship & Install Rack | 1 | 1 | 1 |  | 1000
Install Power cables etc. | 5 | 2 | 10 |  | 250
Prepare Magnet for Testing Period
Vacuum/Cooling | ? | ? |  |  | ?
Current Injection | ? | ? |  |  | ?
Testing of Sub-Station Equipment
Initial tests To prove Equipment is working before Mag field exposure | 1 | 1 | 1 | Estimate £1000/Day | 1000
Testing of Sub-Station Equipment (Over 5 Day Period - As example)
Primary Injection Testing (MCB)- By others | 5 | 1 | 5 | Estimate £1000/Day + test equipment (£2k) | 7000
Equipment Tests | 5 | 1 | 5
Compile data and produce report | 3 | 1 | 3 | Important information is documented
|  | Man days | 49 | Material costs £ | 27854
These manhours/costs are not included in DL MICE project plans
|  |  |  | All man days will be contractor | 14000
Cost £1.2k per week
|  |  |  | Total Costs | 41854
The above costs generate the result of what the minimum level of magnetic field the equipment will withstand before failing
Potential Problems :-
Primary Injection Test Equipment | This equipment maybe susceptible to magnet fields. Can it be mounted at safe enough
distance to remove this issue ? Longer cables may be required
Other Test Equipment | May also be susceptible to magnet fields.
Assumption that internal equipment is protected by panel | If this assumption is wrong then internal equipment that could be affected includes :-
Switches, Fans, Current Transformers, relays and the Main Transformer.
Testing Procedures | These may need to be added too and be of a far longer duration than first anticipated
Residual Magnetic Fields | How to test for this ? Soak period ?
Reliability of Tests | What level of confidence does this testing give with regards to this equipment being exposed
to a magnetic field for long periods of time as would be the case in the MICE hall